## Sheet1
Task: | Worked by: | Date and hour started | Minutes worked |  | Not started | Member | Minutes | Hours
Wireframes | Yu and Georgi | 17.11 ¦¦ 10:50 | 30 | Week 1 | Being worked on | Georgi | 580 | 9:40 | 49%
URS v1 use cases | Ilia and Georgi | 20.11. ¦¦ 16:30 | 40 |  | Completed | Ilia | 513 | 8:33 | 44%
URS v1 GUI | Georgi | 20.11 ¦¦ 13:00 | 20 |  |  | Yu | 80 | 1:20 | 7%
URS v1 NonFunctional | Georgi and Yu | 20.11 ¦¦ 13:30 | 20 |  |  | as a Group | 0 | 0:00 | 0%
URS v1 introduction | Ilia | 20.11. ¦¦ 16:25 | 5 |  |  | Total | 1173 | 19:33
Fix URS mistakes | Georgi and Yu | 24.11 ¦¦ 10:50 | 30 | Week 2
URS v2 use cases | Ilia and Georgi | 25.12. ¦¦ 12:00 | 20
URS v2 NonFunctional | Georgi | 25.12 ¦¦ 13:00 | 5
URS final use cases | Ilia, Georgi | 26.12. ¦¦ 8:30 | 40
URS final GUI | Georgi | 29.12 ¦¦ 12:30 | 10
Design Doc Introduction | Georgi | 01.12 ¦¦ 13:00 | 10 | Week 3
Design Doc Final class diagram | Ilia, Georgi | 03.12 ¦¦ 12:30 | 20
Des Doc Final sequence diagrams | Group | 03.12 ¦¦ 13:00 | 30
Design Doc: Documentation | Ilia | 05.12 ¦¦ 14:00 | 60
App: Create icons | Georgi | 06.12 ¦¦ 14:00 | 30
App: Collision detection | Ilia | 07.12 ¦¦ 13:30 | 30
App: Draw path | Ilia | 08.12 ¦¦ 14:55 | 10 | Week 4
App: Path optimization | Ilia | 10.12. ¦¦ 13:00 | 20
App:Redraw Optimization | Ilia | 10.12. ¦¦ 13:20 | 40
App:Process Flow | Ilia | 11.12. ¦¦ 13:02 | 10
App:Prevent circular | Ilia | 13.12 ¦¦ 15:00 | 5
App: Flow Out-Int | Ilia, Georgi | 13.12 ¦¦ 15:05 | 5
App:Max Flow Capacity | Ilia | 13.12 ¦¦ 15:10 | 5
App: Pipe Safety Limit | Ilia | 13.12 ¦¦ 15:15 | 5
App: ConnectionZone X,Y | Georgi | 15.12 ¦¦ 13:00 | 10 | Week 5
App: Edit Pump | Ilia | 16.12 ¦¦ 14:00 | 5
App: ConnectionZone State | Georgi | 18.12 ¦¦ 13:00 | 60
App: Edit Adjustable | Ilia | 19.12 ¦¦ 13:00 | 5
App: Edit Pipe | Ilia | 19.12 ¦¦ 13:15 | 10
App: Icon below cursor | Georgi | 22.12 ¦¦ 12:00 | 30 | Week 6
App: Colored Icons | Ilia | 22.12 ¦¦ 12:30 | 8
App: Undo/Redo | Ilia | 22.12 ¦¦ 12:38 | 20
App: Save | Yu | 22.12 ¦¦ 13:00
App:Add Element | Ilia | 22.12 ¦¦ 12:58 | 5
App: Remove element | Ilia | 22.12 ¦¦ 13:03 | 5
App: Load | Yu | 25.12 ¦¦ 16:00
App: Add connection | Ilia | 28.12 ¦¦ 15:00 | 10 | Week 7
App:New | Yu | 27.12 ¦¦ 18:00
App: Remove connection | Ilia | 28.12 ¦¦ 15:10 | 10
App: Drag Element | Ilia | 29.12 ¦¦ 12:00 | 20
App: Show Flow over Path | Georgi | 30.12. ¦¦ 12:00 | 60
App: Add Midpoint | Ilia | 30.12. ¦¦ 14:00 | 10
App: Drag Midpoint | Ilia | 30.12. ¦¦ 14:10 | 10
App: Remove Midpoint | Ilia | 30.12. ¦¦ 14:20 | 5
App: RightClick menu | Ilia | 30.12. ¦¦ 14:25 | 10
App: On Hover | Ilia, Georgi | 30.12 ¦¦ 15:00 | 20
App: Show Flow at Sink | Ilia | 30.12 ¦¦ 16:00 | 5
App: Flow angle adjustment | Georgi | 30.12 ¦¦ 17:00 | 120
App: Information box | Ilia | 02.01. ¦¦ 11:20 | 10
App: Final Edit | Ilia | 02.01. ¦¦ 11:30 | 30