## Sheet1
Tasks | Worked by: | Date | Minutes worked |  | Not started | Member | Minutes | Hours
Wireframes | Yu and Georgi | 17/11 | 60 | Week 1 | Being worked on | Georgi | 1110 | 18:30 | 71%
Non func requirements | Georgi and Yu | 17/11 | 40 |  | Completed | Daniel | 0 | 0:00 | 0%
Part of use cases | Georgi | 19/11 | 40 |  |  | Ilia | 240 | 4:00 | 15%
User Interface | Georgi | 20/11 | 30 |  |  | Yu | 220 | 3:40 | 14%
[6 empty] | as a Group | 0 | 0:00 | 0%
[6 empty] | Total | 1570 | 26:10
Fix URS mistakes | Georgi | 24/11 | 30 | Week 2
Class diagram v1 | Georgi and Ilia | 25/11 | 60
URS final | Yu Ilia and Georgi | 26/11 | 120
Class diagram v2 | Ilia and Georgi | 27/11 | 60
Sequence diagram: Add element | Georgi | 02/12 | 60 | Week 3
Introduction to design doc | Georgi | 03/12 | 20
Create element icons | Georgi | 04/12 | 30
Icon below cursor | Georgi | 06/12 | 120
ConnectionZone coordinates | Georgi | 08/12 | 20 | Week 4
ConnectionZone states | Georgi | 11/12 | 120
Flow visualization | Georgi | 16/12 | 120 | Week 5
Flow angle adjustment | Georgi | 18/12 | 180