## Sheet1
Task: | Worked by: | Date and hour started | Minutes worked |  | Not started | Member | Minutes | Hours
URS v1 use cases | Ilia | 20.11. ¦¦ 16:30 | 40 | Week 1 | Being worked on | Georgi | 85 | 1:25 | 14%
URS v1 GUI | Georgi |  |  |  | Completed | Ilia | 513 | 8:33 | 86%
URS v1 NonFunctional | Georgi |  |  |  |  | Yu | 0 | 0:00 | 0%
URS v1 introduction | Ilia | 20.11. ¦¦ 16:25 | 5 |  |  | as a Group | 0 | 0:00 | 0%
URS v2 use cases | Ilia | 01.12. ¦¦ 12:00 | 20 |  |  | Total | 598 | 9:58
URS v2 NonFunctional | Georgi
URS final use cases | Ilia, Georgi | 02.12. ¦¦ 8:30 | 40
URS final GUI | Georgi
Design Doc Final class diagram | Ilia, Georgi | 09.12 ¦¦ 12:30 | 20
Des Doc Final sequence diagrams | Group |  | 30
Design Doc: Documentation | Ilia |  | 60
App: Collision detection | Ilia |  | 30
App: Draw path | Ilia |  | 10
App: Path optimization | Ilia |  | 20
App:Redraw Optimization | Ilia |  | 40
App:Process Flow | Ilia |  | 10
App:Prevent circular | Ilia |  | 5
App: Flow Out-Int | Ilia, Georgi |  | 5
App:Max Flow Capacity | Ilia |  | 5
App: Pipe Safety Limit | Ilia |  | 5
App: Edit Pump | Ilia |  | 5
App: Edit Adjustable | Ilia |  | 5
App: Edit Pipe | Ilia |  | 10
App: Colored Icons | Ilia |  | 8
App: Undo/Redo | Ilia |  | 20
App:Add Element | Ilia |  | 5
App: Remove element | Ilia |  | 5
App: Add connection | Ilia |  | 10
App: Remove connection | Ilia |  | 10
App: Drag Element | Ilia |  | 20
App: Add Midpoint | Ilia |  | 10
App: Drag Midpoint | Ilia |  | 10
App: Remove Midpoint | Ilia |  | 5
App: RightClick menu | Ilia |  | 10
App: On Hover | Ilia, Georgi |  | 20
App: Show Flow at Sink | Ilia |  | 5
App: Show Flow over Path | Georgi
App: Information box | Ilia | 02.01. ¦¦ 11:20 | 10
App: Save | Yu
App: Load | Yu
App:New | Yu
App: Final Edit | Ilia | 02.01. ¦¦ 11:30 | 30